## Design
Tasks | Discipline | Contributors | Due | Priority
Deliverables
Pitch Video and Document | All | All | Week Two
Alpha | All | All | Week Six
Beta | All | All | Week Ten
Gold Master and Final Hand In | All | All | Week Twelve
Design Levels
Level One | Design | Richard Howlett, Paul Hamilton | Week Two | Must
Level Two | Design | Paul Hamilton | Week Five
Level Three | Design | Richard Howlett | Week Five
Design Characters
Hitler | Design | Paul Hamilton | Week Two | Must
Stalin | Design | Richard Howlett | Week Two | Must
Fidel Castro | Design | Richard Howlett | Week Three | Must
Mussolini | Design | Paul Hamilton | Week Three | Must
Julius Caesar | Design | Richard Howlett | Week Three
Kim Jong-Il | Design | Paul Hamilton | Week Three
Robert Mugabe | Design | Richard Howlett | Week Four
Donald Trump | Design | Paul Hamilton | Week Four
Design UI
Main Menu | Design | Paul Hamilton, Richard Howlett | Week Two | Must
Character Selection Menu | Design | Richard Howlett | Week Four | Must
Stage Selection Menu | Design | Richard Howlett | Week Four
In Game HUD | Design | Richard Howlett | Weel Three | Must
Options Menu | Design | Paul Hamilton | Week Four
Controls Menu | Design | Paul Hamilton | Week Four
Match End Menu | Design | Richard Howlett, Paul Hamilton | Week Five | Must
Design Special Moves
Hitler (close) | Design | Paul Hamilton | Week Two | Must
Hitler (far) | Design | Paul Hamilton | Week Two | Must
Stalin (close) | Design | Richard Howlett | Week Two | Must
Stalin (far) | Design | Richard Howlett | Week Two | Must
Fidel Castro (close) | Design | Richard Howlett | Week Three | Must
Fidel Castro (far) | Design | Richard Howlett | Week Three | Must
Mussolini (close) | Design | Paul Hamilton | Week Three | Must
Mussolini (far) | Design | Paul Hamilton | Week Three | Must
Julius Caesar (close) | Design | Richard Howlett | Week Three
Julius Caesar (far) | Design | Richard Howlett | Week Three
Kim Jong-Il (close) | Design | Paul Hamilton | Week Three
Kim Jong-Il (far) | Design | Paul Hamilton | Week Three
Robert Mugabe (close) | Design | Richard Howlett | ]Week Four
Robert Mugabe (far) | Design | Richard Howlett | Week Four
Donald Trump (close) | Design | Paul Hamilton | Week Four
Donald Trump (far) | Design | Paul Hamilton | Week Four
Sound
Menus Background Music | Design | Richard Howlett | Week Six
Level One Music | Design | Richard Howlett | Week Six
Level Two Music | Design | Richard Howlett | Week Seven
Level Three Music | Design | Richard Howlett | Week Seven
Sound Effects | Design | Paul Hamilton | Week Seven
Collision Detection
Platforms | Programming | Andrew Peters, Cameron Wallace | Week Two | Must
Players | Programming | Andrew Peters, Cameron Wallace | Week Four | Must
Moves | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Pickups | Programming | Andrew Peters, Cameron Wallace | Week Four | Must
Screen Boundaries | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Controls
Punch One | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Punch Two | Programming | Andrew Peters, Cameron Wallace | Week Six
Punch Three | Programming | Andrew Peters, Cameron Wallace | Week Eight
Kick One | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Kick Two | Programming | Andrew Peters, Cameron Wallace | Week Six
Kick Three | Programming | Andrew Peters, Cameron Wallace | Week Eight
Jump | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Throw | Programming | Andrew Peters, Cameron Wallace | Week Four
Movement (left and right) | Programming | Andrew Peters, Cameron Wallace | Week Two | Must
Program Special Abilities
Hitler (close) | Programming | Andrew Peters, Cameron Wallace | Week Four | Must
Hitler (far) | Programming | Andrew Peters, Cameron Wallace | Week Four | Must
Stalin (close) | Programming | Andrew Peters, Cameron Wallace | Week Four | Must
Stalin (far) | Programming | Andrew Peters, Cameron Wallace | Week Four | Must
Fidel Castro (close) | Programming | Andrew Peters, Cameron Wallace | Week Six | Must
Fidel Castro (far) | Programming | Andrew Peters, Cameron Wallace | Week Six | Must
Mussolini (close) | Programming | Andrew Peters, Cameron Wallace | Week Six | Must
Mussolini (far) | Programming | Andrew Peters, Cameron Wallace | Week Six | Must
Julius Caesar (close) | Programming | Andrew Peters, Cameron Wallace | Week Six
Julius Caesar (far) | Programming | Andrew Peters, Cameron Wallace | Week Six
Kim Jong-Il (close) | Programming | Andrew Peters, Cameron Wallace | Week Six
Kim Jong-Il (far) | Programming | Andrew Peters, Cameron Wallace | Week Six
Robert Mugabe (close) | Programming | Andrew Peters, Cameron Wallace | Week Six
Robert Mugabe (far) | Programming | Andrew Peters, Cameron Wallace | Week Six
Donald Trump (close) | Programming | Andrew Peters, Cameron Wallace | Week Six
Donald Trump (far) | Programming | Andrew Peters, Cameron Wallace | Week Six
Pickup Coding
Extra health | Programming | Andrew Peters, Cameron Wallace | Week Four
Increase Speed | Programming | Andrew Peters, Cameron Wallace | Week Six
Increase Damage | Programming | Andrew Peters, Cameron Wallace | Week Five
Increase Defence | Programming | Andrew Peters, Cameron Wallace | Week Six
Menu Transitions
Play Button (Main Menu) | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Controls Button (Main Menu) | Programming | Andrew Peters, Cameron Wallace | Week Three
Quit Button (Main Menu) | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Main Menu Button (every stage) | Programming | Andrew Peters, Cameron Wallace | Week Three
Character Select Buttons (character select screen) | Programming | Andrew Peters, Cameron Wallace | Week Six | Must
Rematch Button (End screen) | Programming | Andrew Peters, Cameron Wallace | Week Three
Quit Button (End Screen) | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Back to Character Select Button (End Screen) | Programming | Andrew Peters, Cameron Wallace | Week Six
General Coding
Health | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Damage | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Energy to use special moves | Programming | Andrew Peters, Cameron Wallace | Week Three | Must
Match animations to buttons | Programming | Andrew Peters, Cameron Wallace | Week Four + | Must
Character Modeling
Hitler | Art | Sophie O'neil | Week Four | Must
Stalin | Art | Laura Milkeviciute | Week Four | Must
Fidel Castro | Art | Sophie O'neil | Week Six | Must
Mussolini | Art | Laura Milkeviciute | Week Six | Must
Julius Caesar | Art | Laura Milkeviciute | Week Eight
Kim Jong-Il | Art | Sophie O'neil | Week Eight
Robert Mugabe | Art | Laura Milkeviciute | Week Ten
Donald Trump | Art | Sophie O'neil | Week Ten
Level Creation
Level One | Art | Laura Milkeviciute | Week Four | Must
Level Two | Art | Laura Milkeviciute | Week Seven
Level Three | Art | Laura Milkeviciute | Week Nine
Character Animation Hitler
Idle Animation | Art | Sophie O'Neil | Week Four | Must
Punch One | Art | Sophie O'Neil | Week Four | Must
Punch Two | Art | Sophie O'Neil | Week Four
Punch Three | Art | Sophie O'Neil | Week Four
Kick One | Art | Sophie O'Neil | Week Four | Must
Kick Two | Art | Sophie O'Neil | Week Four
Kick Three | Art | Sophie O'Neil | Week Four
Jump | Art | Sophie O'Neil | Week Four | Must
Walk Left | Art | Sophie O'Neil | Week Four | Must
Walk Right | Art | Sophie O'Neil | Week Four | Must
Throw | Art | Sophie O'Neil | Week Four
Being Thrown | Art | Sophie O'Neil | Week Four
Character Animation Stalin
Idle Animation | Art | Laura Milkeviciute | Week Four | Must
Punch One | Art | Laura Milkeviciute | Week Four
Punch Two | Art | Laura Milkeviciute | Week Four
Punch Three | Art | Laura Milkeviciute | Week Four
Kick One | Art | Laura Milkeviciute | Week Four | Must
Kick Two | Art | Laura Milkeviciute | Week Four
Kick Three | Art | Laura Milkeviciute | Week Four
Jump | Art | Laura Milkeviciute | Week Four | Must
Walk Left | Art | Laura Milkeviciute | Week Four | Must
Walk Right | Art | Laura Milkeviciute | Week Four | Must
Throw | Art | Laura Milkeviciute | Week Four
Being Thrown | Art | Laura Milkeviciute | Week Four
Character Animation Fidel Castro
Idle Animation | Art | Sophie O'Neil | Week Six | Must
Punch One | Art | Sophie O'Neil | Week Six | Must
Punch Two | Art | Sophie O'Neil | Week Six
Punch Three | Art | Sophie O'Neil | Week Six
Kick One | Art | Sophie O'Neil | Week Six | Must
Kick Two | Art | Sophie O'Neil | Week Six
Kick Three | Art | Sophie O'Neil | Week Six
Jump | Art | Sophie O'Neil | Week Six | Must
Walk Left | Art | Sophie O'Neil | Week Six | Must
Walk Right | Art | Sophie O'Neil | Week Six | Must
Throw | Art | Sophie O'Neil | Week Six
Being Thrown | Art | Sophie O'Neil | Week Six
Character Animation Mussolini
Idle Animation | Art | Laura Milkeviciute | Week Six | Must
Punch One | Art | Laura Milkeviciute | Week Six | Must
Punch Two | Art | Laura Milkeviciute | Week Six
Punch Three | Art | Laura Milkeviciute | Week Six
Kick One | Art | Laura Milkeviciute | Week Six | Must
Kick Two | Art | Laura Milkeviciute | Week Six
Kick Three | Art | Laura Milkeviciute | Week Six
Jump | Art | Laura Milkeviciute | Week Six | Must
Walk Left | Art | Laura Milkeviciute | Week Six | Must
Walk Right | Art | Laura Milkeviciute | Week Six | Must
Throw | Art | Laura Milkeviciute | Week Six
Being Thrown | Art | Laura Milkeviciute | Week Six
Character Animation Caesar
Idle Animation | Art | Laura Milkeviciute | Week Eight
Punch One | Art | Laura Milkeviciute | Week Eight
Punch Two | Art | Laura Milkeviciute | Week Eight
Punch Three | Art | Laura Milkeviciute | Week Eight
Kick One | Art | Laura Milkeviciute | Week Eight
Kick Two | Art | Laura Milkeviciute | Week Eight
Kick Three | Art | Laura Milkeviciute | Week Eight
Jump | Art | Laura Milkeviciute | Week Eight
Walk Left | Art | Laura Milkeviciute | Week Eight
Walk Right | Art | Laura Milkeviciute | Week Eight
Throw | Art | Laura Milkeviciute | Week Eight
Being Thrown | Art | Laura Milkeviciute | Week Eight
Character Animation Kim Jong-Il
Idle Animation | Art | Sophie O'Neil | Week Eight
Punch One | Art | Sophie O'Neil | Week Eight
Punch Two | Art | Sophie O'Neil | Week Eight
Punch Three | Art | Sophie O'Neil | Week Eight
Kick One | Art | Sophie O'Neil | Week Eight
Kick Two | Art | Sophie O'Neil | Week Eight
Kick Three | Art | Sophie O'Neil | Week Eight
Jump | Art | Sophie O'Neil | Week Eight
Walk Left | Art | Sophie O'Neil | Week Eight
Walk Right | Art | Sophie O'Neil | Week Eight
Throw | Art | Sophie O'Neil | Week Eight
Being Thrown | Art | Sophie O'Neil | Week Eight
Character Animation Robert Mogabe
Idle Animation | Art | Laura Milkeviciute | Week Ten
Punch One | Art | Laura Milkeviciute | Week Ten
Punch Two | Art | Laura Milkeviciute | Week Ten
Punch Three | Art | Laura Milkeviciute | Week Ten
Kick One | Art | Laura Milkeviciute | Week Ten
Kick Two | Art | Laura Milkeviciute | Week Ten
Kick Three | Art | Laura Milkeviciute | Week Ten
Jump | Art | Laura Milkeviciute | Week Ten
Walk Left | Art | Laura Milkeviciute | Week Ten
Walk Right | Art | Laura Milkeviciute | Week Ten
Throw | Art | Laura Milkeviciute | Week Ten
Being Thrown | Art | Laura Milkeviciute | Week Ten
Character Animation Donald Trump
Idle Animation | Art | Sophie O'Neil | Week Ten
Punch One | Art | Sophie O'Neil | Week Ten
Punch Two | Art | Sophie O'Neil | Week Ten
Punch Three | Art | Sophie O'Neil | Week Ten
Kick One | Art | Sophie O'Neil | Week Ten
Kick Two | Art | Sophie O'Neil | Week Ten
Kick Three | Art | Sophie O'Neil | Week Ten
Jump | Art | Sophie O'Neil | Week Ten
Walk Left | Art | Sophie O'Neil | Week Ten
Walk Right | Art | Sophie O'Neil | Week Ten
Throw | Art | Sophie O'Neil | Week Ten
Being Thrown | Art | Sophie O'Neil | Week Ten
Special Ability Animation
Hitler (close) | Art | Sophie O'Neil | Week Four
Hitler (far) | Art | Sophie O'Neil | Week Four
Stalin (close) | Art | Laura Milkeviciute | Week Four
Stalin (far) | Art | Laura Milkeviciute | Week Four
Fidel Castro (close) | Art | Sophie O'Neil | Week Six
Fidel Castro (far) | Art | Sophie O'Neil | Week Six
Mussolini (close) | Art | Laura Milkeviciute | Week Six
Mussolini (far) | Art | Laura Milkeviciute | Week Six
Julius Caesar (close) | Art | Laura Milkeviciute | Week Eight
Julius Caesar (far) | Art | Laura Milkeviciute | Week Eight
Kim Jong-Il (close) | Art | Sophie O'Neil | Week Eight
Kim Jong-Il (far) | Art | Sophie O'Neil | Week Eight
Robert Mugabe (close) | Art | Laura Milkeviciute | Week Ten
Robert Mugabe (far) | Art | Laura Milkeviciute | Week Ten
Donald Trump (close) | Art | Sophie O'Neil | Week Ten
Donald Trump (far) | Art | Sophie O'Neil | Week Ten